## Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
SPRINT 5
SPRINT 6
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION (In Days) | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Requirements Analysis |  | 20 | 20 | 0 |  |  |  | 5 | 100%
1.1 | Get all the research articles for the problem | Mahesh | 2 | 2 | 0 | 1 | 2022-12-26 | 2022-12-26 | 1 | 100% | bar: WEEK 1 M
1.2 | Study and Deep dive in all the articles | Asffand & Mahesh | 10 | 10 | 0 | 1 | 2022-12-27 | 2022-12-28 | 2 | 100% | bar: WEEK 1 T to WEEK 1 W
1.3 | Data set gathering | Mahesh | 3 | 3 | 0 | 1 | 2022-12-29 | 2022-12-29 | 1 | 100% | bar: WEEK 1 T
1.4 | Data cleaning | Mahesh | 5 | 5 | 0 | 1 | 2022-12-30 | 2022-12-30 | 1 | 100% | bar: WEEK 1 F to WEEK 2 F
2 | Data Analysis |  | 24 | 24 | 0 |  |  |  | 8 | 100%
2.1 | Exploratory Data Analysis | Mahesh | 15 | 15 | 0 | 1 | 2023-01-02 | 2023-01-06 | 5 | 100%
2.2 | One Hot Encoding | Asffand | 3 | 3 | 0 | 2 | 2023-01-09 | 2023-01-09 | 1 | 100% | bar: WEEK 2 M to WEEK 3 M
2.3 | Label Encoding | Mahesh | 2 | 2 | 0 | 2 | 2023-01-10 | 2023-01-10 | 1 | 100% | bar: WEEK 3 T
2.4 | Feature Selection and Scaling | Mahesh | 4 | 4 | 0 | 2 | 2023-01-11 | 2023-01-11 | 1 | 100% | bar: WEEK 3 W
3 | Machine learning models Implementation and Testing |  | 64 | 64 | 0 |  |  |  | 23 | 100%
3.1 | K-Nearest Neighbours | Mahesh | 15 | 15 | 0 | 2 | 2023-01-12 | 2023-01-20 | 7 | 100% | bar: WEEK 3 T to WEEK 5 F
3.2 | Logistic Regression | Asffand | 13 | 13 | 0 | 2 | 2023-01-23 | 2023-01-26 | 4 | 100%
3.3 | Decision Tree | Mahesh | 13 | 13 | 0 | 3 | 2023-01-27 | 2023-02-01 | 4 | 100% | bar: WEEK 5 M to WEEK 6 W
3.4 | Gradient Boosting | Asffand | 17 | 17 | 0 | 3 | 2023-02-02 | 2023-02-09 | 6 | 100% | bar: WEEK 6 T to WEEK 7 T
3.5 | Classification Reports | Asffand | 6 | 6 | 0 | 3 | 2023-02-10 | 2023-02-13 | 2 | 100% | bar: WEEK 7 F to WEEK 8 F
4 | Front end and Web server Building |  | 27 | 27 | 0 |  |  |  | 15 | 100%
4.1 | Build a module to save all the pre trained models | Mahesh | 6 | 6 | 0 | 4 | 2023-02-14 | 2023-02-17 | 4 | 100%
4.2 | Develop HTML pages for the web pages | Asffand | 13 | 13 | 0 | 4 | 2023-02-20 | 2023-02-24 | 5 | 100% | bar: WEEK 8 M to WEEK 9 F
4.3 | Develop and add style sheets for the web page | Mahesh | 5 | 5 | 0 | 5 | 2023-02-27 | 2023-03-01 | 3 | 100% | bar: WEEK 8 W to WEEK 8 F; WEEK 10 M to WEEK 10 W
4.4 | Develop interaction between flask development server and web browser | Asffand | 3 | 3 | 0 | 5 | 2023-03-02 | 2023-03-06 | 3 | 100% | bar: WEEK 8 M; WEEK 8 W to WEEK 8 F; WEEK 10 T to WEEK 11 F
5 | Deployment,Testing and Analysis |  | 34 | 34 | 0 |  |  |  | 19 | 100%
5.1 | Testing web app locally | Asffand | 8 | 8 | 0 | 6 | 2023-03-07 | 2023-03-08 | 2 | 100%
5.2 | Deploy the web app on AWS cloud and run it. | Mahesh | 7 | 7 | 0 | 6 | 2023-03-09 | 2023-03-13 | 3 | 100% | bar: WEEK 8 T to WEEK 8 F; WEEK 11 W to WEEK 12 M
5.3 | Acceptance Testing | Mahesh | 19 | 19 | 0 | 6 | 2023-03-14 | 2023-03-17 | 4 | 100% | bar: WEEK 11 W to WEEK 11 F; WEEK 12 T to WEEK 12 F
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS worked in total (if we worked the same day we count it as 1 day) | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 169 | 169 | 0 | 70 | 2.4143 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 169 | 169 | 169 | 169 | 166.5857 | 164.1714 | 161.7571 | 159.3429 | 156.9286 | 154.5143 | 152.1 | 149.6857 | 147.2714 | 144.8571 | 142.4429 | 140.0286 | 137.6143 | 135.2 | 132.7857 | 130.3714 | 127.9571 | 125.5429 | 123.1286 | 120.7143 | 118.3 | 115.8857 | 113.4714 | 111.0571 | 108.6429 | 106.2286 | 103.8143 | 101.4 | 98.9857 | 96.5714 | 94.1571 | 91.7429 | 89.3286 | 86.9143 | 84.5 | 82.0857 | 79.6714 | 77.2571 | 74.8429 | 72.4286 | 70.0143 | 67.6 | 65.1857 | 62.7714 | 60.3571 | 57.9429 | 55.5286 | 53.1143 | 50.7 | 48.2857 | 45.8714 | 43.4571 | 41.0429 | 38.6286 | 36.2143 | 33.8 | 31.3857 | 28.9714 | 26.5571 | 24.1429 | 21.7286 | 19.3143 | 16.9 | 14.4857 | 12.0714 | 9.6571
[10 empty] | ESTIMATE | 169 | 167 | 162 | 157 | 154 | 149 | 146 | 143 | 140 | 137 | 134 | 132 | 129 | 127 | 123 | 120 | 118 | 118 | 115 | 115 | 112 | 107 | 104 | 103 | 97 | 94 | 89 | 89 | 87 | 82 | 80 | 76 | 71 | 70 | 65 | 63 | 59 | 56 | 53 | 53 | 49 | 47 | 44 | 42 | 38 | 33 | 33 | 27 | 26 | 23 | 18 | 16 | 14 | 12 | 9 | 4 | 0 | 0 | -4 | -10 | -12 | -15 | -19 | -23 | -26 | -29 | -31 | 10 | 7 | 3 | 4153
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | 2 | 5 | 5 | 3 | 5 | 3 | 3 | 3 | 3 | 3 | 2 | 3 | 2 | 4 | 3 | 2 | 0 | 3 | 0 | 3 | 5 | 3 | 1 | 6 | 3 | 5 | 0 | 2 | 5 | 2 | 4 | 5 | 1 | 5 | 2 | 4 | 3 | 3 | 0 | 4 | 2 | 3 | 2 | 4 | 5 | 0 | 6 | 1 | 3 | 5 | 2 | 2 | 2 | 3 | 5 | 4 | 0 | 4 | 6 | 2 | 3 | 4 | 4 | 3 | 3 | 2 | 3 | 3 | 4 | 3 | 169
[10 empty] | HRS REMAINING | 167 | 162 | 157 | 154 | 149 | 146 | 143 | 140 | 137 | 134 | 132 | 129 | 127 | 123 | 120 | 118 | 118 | 115 | 115 | 112 | 107 | 104 | 103 | 97 | 94 | 89 | 89 | 87 | 82 | 80 | 76 | 71 | 70 | 65 | 63 | 59 | 56 | 53 | 53 | 49 | 47 | 44 | 42 | 38 | 33 | 33 | 27 | 26 | 23 | 18 | 16 | 14 | 12 | 9 | 4 | 0 | 0 | -4 | -10 | -12 | -15 | -19 | -23 | -26 | -29 | -31 | -34 | 7 | 3 | 0 | 3952
WEB IMPLEMENTATION FOR PREDICTING ELIGIBLE CUSTOMERS USING MACHINE LEARING AND AWS