## User Stories
EPIC | USER STORY | PRIORITY | VALUE | RISK | ESTIMATE | RELEASE | DESCRIPTION | DEPENDENCIES | PRIORITY(INT) | VALUE(INT) | RISK(INT) | PRIORITY(INV) | VALUE(INV) | RISK(INV) | THEME(Sp) | FEATURE(Sp) | RELEASE(S) | ROW(S)
Requirements Gathering | Get all the research articles required for the project. | 2 Med | 1 High | 4 Low | SM | 1.x | We have discovered all the articles that are useful for implementing the project. | All the resoucres has been taken from the internet
Requirements Gathering | Study all the articles and their implementation methods | 2 Med | 1 High | 2 Med | SM | 1.x | We have studied all the articles from the resources. | We have taken idea from the research papers | 2 | 1 | 2 | 3 | 4 | 3 |  |  | 1.x | 3
Data Analysis | To download the the data set and let the data ready for training and testing. | 1 High | 1 High | 2 Med | MD | 1.x | Downloaded the dataset from kaggle.com | Dataset has been downloaded from kaggle.
Data Analysis | To Perform explorartory data analysis for the downloaded dataset using feature selection and scaling | 1 High | 1 High | 2 Med | MD | 1.x | To clean the data using different techniques like feature selection and scaling. | Dataset downloaded from kaggle | 1 | 1 | 2 | 4 | 4 | 3 |  |  | 1.x | 5
Data Analysis | To Perform data analysis for the downloaded dataset using onehot encoding and label encoding | 1 High | 1 High | 2 Med | MD | 1.x | To clean the data removingthe noise using one hot encoding and label encoding for model training and testing. | Dataset downloaded from kaggle | 1 | 1 | 2 | 4 | 4 | 3 |  |  | 1.x | 6
Machine Learning Models Implementation | List the ML Models and their dependencies which are to be implemented. | 2 Med | 2 Med | 1 High | MD | 1.x | List down the models and dependencies which are implemeneted the project. | Machine Learning like Logistric regression Decision tree we have implented in our project
Machine Learning Models Implementation | Logistic Regression Model Implementation. | 1 High | 1 High | 1 High | LG | 1.x | Build logistic regresssion model using the dataset. | Data set and Jupyter notebook with all the libraries installed. | 1 | 1 | 1 | 4 | 4 | 4 |  |  | 1.x | 8
Machine Learning Models Implementation | Decision Tree Classifier Model Implementation. | 1 High | 1 High | 1 High | LG | 1.x | We have used Decision Tree Classifier in our project to obtaining all possible solution to an issue based on constraints. Because the model's depiction resembles a tree, it is known as a decision tree. It uses for asking the loan approved or not | Dataset and Jupyter notebook with all the libraries installed. | 1 | 1 | 1 | 4 | 4 | 4 |  |  | 1.x | 9
Machine Learning Models Implementation | K Nearest Neighbour Model Implementation | 1 High | 2 Med | 1 High | XLG | 1.x | Build the KNN Model usingthe data set which gives better accuracy. It is robust to the noisy training data. It can be more effective if the training data is large. | Dataset and Jupyter notebook with all the libraries installed. | 1 | 2 | 1 | 4 | 3 | 4 |  |  | 1.x | 10
Model Testing and Evaluation | To Test and Evaluate all the models that are build. | 2 Med | 1 High | 1 High | LG | 1.x | Test and evaluate all models which are implemented. | Logistic regression , Decision Tree and K Nearest Neighbours models | 2 | 1 | 1 | 3 | 4 | 4 |  |  | 1.x | 11
Model Testing and Evaluation | To Test the Logistic regression Model and evaluate it. | 2 Med | 1 High | 2 Med | LG | 1.x | It is used to calculate or predict the probability of a binary (yes/no) event occurring. In this project we check if the person gets a loan or not. | Logistic regresssion trained model in jupyter notebook. | 2 | 1 | 2 | 3 | 4 | 3 |  |  | 1.x | 12
Model Testing and Evaluation | To Test the decision tree classifier and evaluate it. | 2 Med | 1 High | 3 Med | LG | 1.x | It is most commonly used for classification. It is a tree-structured classifier in which internal nodes reflect dataset characteristics, branches represent judgment criteria, and each leaf node symbolizes the result. it uses for asking the loan approved or not | Decision Tree trained model in jupyter notebook. | 2 | 1 | 3 | 3 | 4 | 2 |  |  | 1.x | 13
Model Testing and Evaluation | To Test the K Nearest Neighbors Model and evaluate it. | 2 Med | 2 Med | 2 Med | LG | 1.x | To test the model which saves the dataset and then classifies it into a categorization that is very comparable to the new data. It is robust to the noisy training data It can be more effective if the training data is large. | KNN trained model in jupyter notebook. | 2 | 2 | 2 | 3 | 3 | 3 |  |  | 1.x | 14
Front end App Development | To build HTML page for the index page. | 2 Med | 2 Med | 2 Med | MD | 1.x | To develop a customized HTML page with form for collecting the data and predicting the result in the web. | web page where customer can fill the given details and then wait for the predicted output. | 2 | 2 | 2 | 3 | 3 | 3 |  |  | 1.x | 15
Front end App Development | To devlop a HTML page for the approved and rejected screens. | 2 Med | 2 Med | 2 Med | MD | 1.x | To develpoed HTML pages for the customer to check the eligibility of loan when accepted or rejected. | HTML Pages are developed for web pages. | 2 | 2 | 2 | 3 | 3 | 3 |  |  | 1.x | 16
Front end App Development | To add CSS layouts for the page | 2 Med | 2 Med | 2 Med | MD | 1.x | To add styles for the index page. | HTML pages | 2 | 2 | 2 | 3 | 3 | 3 |  |  | 1.x | 17
Font end App Development | To build a pickle file with all the pre trained ML models. | 1 High | 1 High | 1 High | MD | 1.x | To build a file which stores all the pre traind Machine learning models data and prediction result. | ML models implementation | 1 | 1 | 1 | 4 | 4 | 4 |  |  | 1.x | 18
Web Server Building | To build a Flask web server and host it on the web browser. | 1 High | 1 High | 2 Med | SM | 1.x | To build a flask web server using python for hosting the web page and displaying the prediction result. | Web page with ML models | 1 | 1 | 2 | 4 | 4 | 3 |  |  | 1.x | 19
Web Server Building | To Verify the interaction between Web browser and Flask development server | 1 High | 1 High | 2 Med | SM | 1.x | To Verfiy the Get and Post method interactions between the Web server and browser. | Needs to open the application | 1 | 1 | 2 | 4 | 4 | 3 |  |  | 1.x | 20
Web Server Building | To verify the implementation on local machine. | 1 High | 1 High | 2 Med | MD | 1.x | To Test the implementation and check whether we get the expected result or not. | ML models with flask web server. | 1 | 1 | 2 | 4 | 4 | 3 |  |  | 1.x | 21
Deployment and Analysis | To deploy the web application in AWS cloud. | 2 Med | 1 High | 1 High | LG | 1.x | To deploy the Project to AWS EC2 and test the expected result. | ML models with flask web server in AWS EC2. | 2 | 1 | 1 | 3 | 4 | 4 |  |  | 1.x | 22
Deployment and Analysis | Verify whether app can be deployed and interacted using browser and Flask Server. | 1 High | 1 High | 2 Med | MD | 1.x | An application has been verified and deployed using browser and flask server in our project | ML models with flask web server. | 1 | 1 | 2 | 4 | 4 | 3 |  |  | 1.x | 23
Deployment and Analysis | Verify the application is running successfully post deployment. | 1 High | 1 High | 2 Med | MD | 1.x | To test Application run successfully, so that Customer can check eligibility of the loan |  | 1 | 1 | 2 | 4 | 4 | 3 |  |  | 1.x | 24
Deployment and Analysis | Verify and analyse the output with different types of data. | 2 Med | 1 High | 2 Med | MD | 1.x | We have verified with different attributes of customer along with dataset |  | 2 | 1 | 2 | 3 | 4 | 3 |  |  | 1.x | 25
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0